## 2024 (hidden)
Date of end of week | 2024-04-19 | 2024-04-26 | 2024-05-03 | 2024-05-10 | 2024-05-17 | 2024-05-24 | 5/31-JT Vaca | 6/7-JT Vaca | 2024-06-14 | 2024-06-21 | 2024-06-28 | 2024-07-05 | 2024-07-12 | 2024-07-19 | 2024-07-26 | 2024-08-02 | 2024-08-09 | 2024-08-16 | 2024-08-23 | 2024-08-30 | 2024-09-06 | 2024-09-13 | 2024-09-20 | 9/27/2024 Hurrican Helen off hlaf week | 2024-10-04 | 10/11/2024 Hurricane Milton off after mon at 3 all week | 10/18/2024 no power mon 10/14 | 2024-10-25 | 2024-11-01 | 2024-11-08 | 2024-11-15 | 2024-11-22 | 11/29/2024- thanksgiving on thur | 2024-12-06 | 2024-12-13 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-01-10
Lamination--Schedule |  |  | 40-18 | 40-18 | 40-19 |  |  |  | 2024-07-05: 40-19 small parts in house; 2024-07-26: 40-20 tubs in hoiuse; 2024-08-16: 40-20 small parts in house; 2024-09-13: 40-21 tubs in house |  |  | 40-20 small parts in house |  |  |  | 40-22 tubs in house |  |  |  | 40-22 small parts in house |  |  |  | 40-23 tubs in house
Lamination-Actual |  |  | 40-18 | 40-18 | 40-19 |  |  |  | 2024-07-05: 40-19 small parts in house; 2024-08-09: 40-20 tubs in house; 2024-08-16: 40-20 small parts in house; 2024-08-23: 40-20 small parts in house; 2024-09-13: 40-21 tubs in house |  |  | 40-21 tubs in house |  | 40-21 small parts in house | 40-21 tubs finish and build floor fishboxes |  |  | 40-20 console liner 40-22 tubs | 40-20 anchor hatch
Assembly-Scheduled |  |  | 40-18 | 40-18 | 40-18 | 40-18 | 40-18 | 40-19 not here | 40-19 here @ end week | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-21 | 40-21 | 40-21 | 40-21 | 40-21 | 40-21 | 40-21 | 40-21 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22
Assembly-Actual |  |  | 40-18 | 40-18 | 40-18 | 40-18 | 40-18 | 40-19 not here | 40-19 here @ end week | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 40-21 | 40-21- deck and liner | 40-21- deck and liner | 40-21 hull here 12/5/24 | 40-21 | 40-21 | 40-21 | 40-21 | 40-21
Finishing-Scheduled |  |  | 40-16 qc | 40-18 | 40-18 | 40-18 | 40-18 | 40-18 boat | 40-18 boat | 40-18 boat | 40-18 boat | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 40-20 tubs | 40-19 | 40-19 | 40-19 | 40-20 | 40-20 | 40-20 | 40-20 40-21 tubs | 40-20 | 40-20 | 40-20 | 40-20 | 40-21 | 40-21 | 40-21 | 40-21 | 40-21 | 40-21 | 40-21 | 40-21 | 40-22 | 40-22 | 40-22 | 40-22
Finishing-Actual |  |  | 40-16 qc | 40-18 | 40-18 | 40-18 | 40-18 | 40-18 boat | 40-18 boat | 40-18 boat | 40-18 boat | 40-19 | 40-19 | 40-19 | 40-18 stuff meyers | 40-19 rear deck and 40-18 hatches | 40-19 not touched | 40-19-nothing has been touched still need parts back | 40-18 40-19-HT only | 40-18-hatches, pieplate, splashwell 40-19-all parts we have | 40-19 40-20 tubs | 40-19 | 40-19 | 40-20 small parts | 40-20 small parts | 40-20 small parts | 40-20 small parts | 40-20-small parts 40-19 hull | 40-20-small parts 40-19 | 40-20-small parts 40-19 hull | 40-20-small parts 40-21 tubs 40-19 | 40-20-small parts 40-21 tubs 40-19 | 40-20 hull | 40-20 hull | 40-20 hull | 40-21 40-22 tubs | 40-21 | 40-21 | 40-21
Rigging-Scheduled | 40-16 | 40-16 | 40-16 finish | 40-16 finish | 40-17 | 40-17 | 40-17 | 40-17 | 40-17 | 40-17 | 40-17 | 40-18 | 40-18 | 40-18 | 40-18 | 40-18 | 40-18 | 40-18 | 40-18 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-21 | 40-21 | 40-21 | 40-21
Rigging-Actual | 40-16 | 40-16 | 40-16 finish | 40-16 finish | 40-17 | 40-17 | 40-17 | 40-17 | 40-17 | 40-17 | 40-17 | 40-18 | 40-18 | 40-18 | 40-18-1st full week | 40-18 | 40-18 | 40-18 | 40-18 | 40-18 | 40-18 | 40-18 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-19 | 40-20 | 40-20 | 40-20 | 40-20
Seatrial/qc-Scheduled |  | 40-16 aeat trial on thur | 40-16 | 40-16 |  |  |  |  | 2024-07-05: 40-17; 2024-07-12: 40-17; 2024-07-19: 40-17; 2024-08-30: 40-18; 2024-09-06: 40-18 |  |  |  |  | 40-19 | 40-19 | [6 empty] | 40-20 | 40-20 | 40-20
Seatrial/qc-Actual |  | 40-16 aeat trial on thur | 40-16 | 40-16 |  |  |  |  | 2024-07-05: 40-17; 2024-07-12: 40-17; 2024-07-19: 40-17; 2024-09-13: 40-18; 2024-09-20: 40-18 | [10 empty] | 40-19
Detail/Delivery-Scheduled |  |  |  | 40-16 |  |  |  |  | 2024-07-19: 40-17; 2024-07-26: 40-17; 2024-09-13: 40-18 | [6 empty] | 40-19
Detail/Delivery-Actual |  |  |  | 40-16 |  |  |  |  | 2024-07-19: 40-17; 2024-07-26: 40-17; 2024-09-20: 40-18 | [12 empty] | 40-19
Date of end of week | 2024-04-19 | 2024-04-26 | 2024-05-03 | 2024-05-10 | 2024-05-17 | 2024-05-24 | 5/31-JT Vaca | 6/7-JT Vaca | 2024-06-14 | 2024-06-21 | 2024-06-28 | 2024-07-05 | 2024-07-12 | 2024-07-19 | 2024-07-26 | 2024-08-02 | 2024-08-09 | 2024-08-16 | 2024-08-23 | 2024-08-30 | 2024-09-06 | 2024-09-13 | 2024-09-20 | 2024-09-27 | 2024-10-04 | 2024-10-11 | 2024-10-18 | 2024-10-25 | 2024-11-01 | 2024-11-08 | 2024-11-15 | 2024-11-22 | 2024-11-29 | 2024-12-06 | 2024-12-13 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-01-10
Lamination-Scheduled | Cephuraun | Cephuraun/ Winterhalter tubs | Winterhalter tubs/llp/small | Winterhalter deck/liner | Winterhalter/ Meyers | Meyers tubs/lp/small | Meyers deck/liner | Meyers/ DeMarco | DeMarco | DeMarco | Catch up on parts start on Jefferies | Jefferies | Jefferies | Jefferies | Donatucci | Donatucci | Lemasney | Lemasney | Lemasney | Parr | Parr | Parr | Fisher | Fisher | Fisher | Sheffield | Sheffield | Sheffield | Songy | Songy | Songy | Sims | Sims | Sims | delgado | delgado | delgado | delgado | delgado
Lamination-Actual | Cephuraun | Cephuraun/ Winterhalter tubs | Winterhalter tubs/llp/small | Winterhalter deck/liner | Winterhalter/ Meyers | Meyers tubs/lp/small | Meyers deck/liner | Meyers/ DeMarco | DeMarco | DeMarco | Catch up on parts start on Jefferies | Jefferies | Jefferies | Jefferies | Donatucci | Donatucci | Lemasney | Lemasney | Lemasney-behind on console and lp | Parr | Parr | Parr | Fisher | Fisher | Fisher | Sheffield | Sheffield | Sheffield | Sheffield fisher stringer lemasney top | Sheffield fisher stringer/hull | Sheffield fisher stringer/hull parr top Shefield-stringers | Songy small parts Shefield-hull | Songy deck/liner Shefield-hull/stringer | Songy deck/liner/small parts songy-stringers sheffield top | Goldman songy-hull | Goldman songy hull/stringer | Goldman sims-stringers | Goldman | Goldman
Assembly-Scheduled | Wilson | Wilson | Cephuraun | Cephuraun | Cephuraun | Winterhalter | Winterhalter | Winterhalter | Meyers | Meyers | Meyers | DeMarco | DeMarco | DeMarco | Demarco/Jefferies | Jefferies | Jefferies | Donatucci | Donatucci | Donatucci | Lemasney | Lemasney | Lemasney | Parr | Parr | Parr | Fisher | Fisher | Sheffield | Sheffield | Sheffield | Songy | Songy | Songy | Sims | Sims | Sims | delgado | delgado
Assembly-Actual | Wilson | Wilson | Cephuraun | Cephuraun | Cephuraun | Winterhalter | Winterhalter | Winterhalter | Meyers | Meyers | Meyers | DeMarco | DeMarco | DeMarco | Demarco/Jefferies | Jefferies | Jefferies | Jefferies | Donatucci | Donatucci | Donatucci started on lemasney | Lemasney | Lemasney | Lemasney | Parr | Parr | Parr | Parr | Parr/fisher tubs | Parr -wed Fisher | Fisher-hull pulledm11/14 | Fisher | Fisher | Sheffield | Sheffield | Sheffield | Sheffield | Somgy | Somgy
Finishing-Scheduled | Faccibene | Wilson-small Ceph-tubs | Wilson | Wilson | Cephuraun small | Cephuraun | Cephuraun | Winterhalter small | Winterhalter | Winterhalter | Meyers small | Meyers | Meyers | DeMarco small | DeMarco | DeMarco Jefferys tubs | Jefferies | Jefferies | Jefferies | Donatucci | Donatucci | Donatucci | Lemasney | Lemasney | Lemasney | Parr | Parr | Parr | Fisher | Fisher | Fisher | Sheffield | Sheffield | Sheffield | Songy | Songy | Songy | Sims | Sims
Finishing-Actual | Faccibene | Wilson-small Ceph-tubs | Wilson | Wilson | Cephuraun small | Cephuraun | Cephuraun | Winterhalter small | Winterhalter | Winterhalter | Meyers small | Meyers | Meyers | DeMarco small | Meyers/Demarco | DeMarco | DeMarco small parts | DeMarco | DeMarco | DeMarco jefferies | Jefferies Lemasney tubs | Jefferies | Donatucci | Donatucci parr tubs | Donatucci | Lemasney | Lemasney fisher tubs | Lemasney | Lemasney | Lemasney-wed Parr | Parr | Parr | Fisher mid week | Fisher | Fisher | Fisher | Sheffield | Sheffield | Sheffield
Rigging-Scheduled | Lynch fac-small | Faccibene | Faccibene | Wilson small | Wilson | Wilson | Cephuraun small | Cephuraun | Cephuraun | Winterhalter small | Winterhalter | Winterhalter | Meyers small | Meyers | Meyers | DeMarco small | DeMarco | DeMarco | Jefferies | Jefferies | Jefferies | Donatucci | Donatucci | Donatucci | Lemasney | Lemasney | Lemasney | Parr | Parr | Parr | Fisher | Fisher | Fisher | Sheffield | Sheffield | Sheffield | Sheffield
Rigging-Actual | Lynch fac-small | Faccibene | Faccibene | Wilson small | Wilson | Wilson | Cephuraun small | Cephuraun | Cephuraun | Winterhalter small | Winterhalter | Winterhalter | Meyers small | Meyers | Meyers-1st week boat not in as of 7/23, console liner and uperstation and top | Meyers | Meyers | DeMarco small parts | DeMarco | DeMarco | DeMarco | DeMarco | Jefferies | Jefferies | Jefferies/ Donatucci console started | Jefferies/ Donatucci console-mon 10/7-till 3 | Donatucci | Donatucci | Donatucci | Lemasney- console and liner 11/5 | Lemasney | Lemasney | Lemasney | Lemasney/ Parr | Parr | Parr | Fisher | Fisher | Fisher
Seatrial/qc-Scheduled | Lynch | Lynch |  | Faccibene |  |  | Wilson |  | 2024-06-21: Cephuraun; 2024-07-12: Winterhalter; 2024-07-19: Winterhalter; 2024-08-02: Meyers; 2024-08-23: DeMarco; 2024-09-13: Jefferies; 2024-10-04: Donatucci; 2024-10-25: Lemasney; 2024-11-15: Parr; 2024-12-06: Fisher; 2024-12-27: Sheffield
Seatrial/qc-Actual | Lynch | Lynch |  | Faccibene |  |  | Wilson |  | 2024-06-21: Cephuraun; 2024-07-12: Winterhalter; 2024-07-19: Winterhalter; 2024-07-26: Winterhalter; 2024-08-09: Meyers; 2024-09-13: DeMarco; 2024-10-25: Jefferies; 2024-11-01: Jefferies; 2024-11-08: Donatucci; 2024-11-29: Lemasney; 2024-12-20: Parr; 2025-01-10: Fisher
Detail/Delivery-Scheduled |  | Lynch |  |  | Faccibene |  |  | Wilson | 2024-06-28: Cephuraun; 2024-07-19: Winterhalter; 2024-07-26: Winterhalter; 2024-08-09: Meyers; 2024-08-30: DeMarco; 2024-09-20: Jefferies; 2024-10-11: Donatucci; 2024-11-01: Lemasney; 2024-11-22: Parr; 2024-12-20: Fisher
Detail/Delivery-Actual |  | Lynch |  |  | Faccibene |  |  | Wilson | 2024-06-28: Cephuraun; 2024-07-19: Winterhalter; 2024-07-26: Winterhalter; 2024-08-16: Meyers; 2024-09-27: DeMarco; 2024-11-08: Jefferies; 2024-11-15: Donatucci; 2024-12-06: Lemasney; 2024-12-20: Parr

## 2025
Date of end of week | 12/27/2024 work 23,26,27 | 1/3/2025 work 30,2,3 | 1/10 | 1/17 | 1/24 | 1/31 | 2/7 | 2/14 | 2/21 | 2/28 | 3/7 | 3/14 | 3/21 | 3/28 | 4/4 | 4/11 | 4/18 | 4/25 | 4/28-5/2 | 5/5-5/9 | 5/12-5/16 | 5/19-5/23 | 5/26-lmemorial day 5/27-5/30 | 6/2-6/6 | 6/9-6/13 | 6/16-6/20 | 6/23-6/27 | 6/30-7/4 JT gone 6/30 | 7/7 off 7/8-massive clean up 7/9-7/11 | 7/14-7/18 | 7/21-7/25 | 7/28-8/1 | 8/4-8/8 | 8/11-8/15 | 8/18-8/22 | 8/25-8/29 | 9/2-9/5 | 9/8-9/12 | 9/15-9/19 | 9/22-9/26 | 9/29-10/3 | 10/6-10/10 | 10/13-10/17 | 10/20-10/24 | 10/27-10/31 | 11/3-11/7 | 11/10-11/14 | 11/17-11/21 | 11/24-11/26 | 12/1-12/5 | 12/08-12/12 | 12/15-12/19 | 12/22 & 12/23 | 12/29 & 12/30 | 1/5/26-1/9/26 | 1/12/2026-1/16/27 | 1/19/26-1/23/26 | 1/26/26-1/30/26 | 2/2-2/6 | 2/9-2/13 | 2/16-2/20 | 2/23-2/27 | 3/2-3/6 | time axis 2026-03-09 to 2026-12-28
Lamination--Schedule |  |  |  | 40-23 tubs in house |  |  |  | 40-23 small parts in house |  |  |  | 40-24 tubs in house |  |  |  | 40-24 small parts in house |  |  |  | 40-25 tubs in house |  |  |  | 40-25 small parts in house |  |  |  | 40-26 tubs in house |  |  |  | 40-26 small parts in house |  |  |  | 40-27 tubs in house |  |  |  | 40-27 small parts in house |  |  |  | 40-28 tubs in house |  |  |  | 40-28 small parts in house |  |  |  |  | 40-26 deck boat | 40-26 deck boat | 40-26 deck boat | 40-26 deck boat |  |  |  | 40-27 | 40-27 | 40-27 | 40-27 | 2026-03-30: 40-28; 2026-04-06: 40-28; 2026-04-13: 40-28; 2026-04-20: 40-28; 2026-05-18: 40-29; 2026-05-25: 40-29; 2026-06-01: 40-29; 2026-06-08: 40-29; 2026-07-06: 40-30; 2026-07-13: 40-30; 2026-07-20: 40-30; 2026-07-27: 40-30; 2026-08-24: 40-31; 2026-08-31: 40-31; 2026-09-07: 40-31; 2026-09-14: 40-31; 2026-10-12: 40-32; 2026-10-19: 40-32; 2026-10-26: 40-32; 2026-11-02: 40-32; 2026-11-30: 40-28; 2026-12-07: 40-28; 2026-12-14: 40-28; 2026-12-21: 40-28
Lamination-Actual | [15 empty] | 40-23 | [13 empty] | 40-23 need to start thinking small parts |  | Hull ready 8/1 | 40-23 LP | 40-23 Finish LP Hardtop | 40-23 finish things | 40-23 small parts thin skin for hardtop | 40-23 small parts | 40-23 small parts |  | 40-24 need to start thnking small parts | 40-24 need to start thnking small parts | 40-24 need to start thnking small parts | 40-24 need to start thnking small parts | 40-24 need to start thnking small parts | 40-24 need to start thnking small parts |  |  | 40-25 | 40-25 | 40-25 | 40-25 |  |  |  | 40-26 deck boat | 40-26 deck boat | 40-26 deck boat | 40-26 deck boat |  |  |  | 40-27 | 40-27 | 2026-03-09: 40-27; 2026-03-16: 40-27; 2026-04-13: 40-28; 2026-04-20: 40-28; 2026-04-27: 40-28; 2026-05-04: 40-28; 2026-06-01: 40-29; 2026-06-08: 40-29; 2026-06-15: 40-29; 2026-06-22: 40-29; 2026-07-20: 40-30; 2026-07-27: 40-30; 2026-08-03: 40-30; 2026-08-10: 40-30; 2026-09-07: 40-31; 2026-09-14: 40-31; 2026-09-21: 40-31; 2026-09-28: 40-31; 2026-10-26: 40-32; 2026-11-02: 40-32; 2026-11-09: 40-32; 2026-11-16: 40-32; 2026-12-14: 40-28; 2026-12-21: 40-28; 2026-12-28: 40-28 | 40-28
Assembly-Scheduled | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 | 40-23 | 40-23 | 40-23 | 40-23 | 40-23 | 40-23 | 40-23 | 40-23 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 |  | 40-26 hull | 40-26 deck boat | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-29 | 40-29 | 40-29 | 40-29 | 40-29 | 40-29 | 40-29 | 40-30 | 40-30 | 40-30 | 40-30 | 40-30 | 40-30 | 40-30 | 40-31 | 40-31 | 40-31 | 40-31 | 40-31 | 40-31 | 40-31 | 40-32 | 40-32 | 40-32 | 40-32 | 40-32 | 40-32 | 40-32 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28
Assembly-Actual | 40-21 | 40-21 | 40-21 | 40-21 | 40-21 | 40-21-decked | 40-21 | 40-21 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 hull on wed 3/26 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 | 40-23 | 40-23 | 40-23 |  |  |  | 40-23 deck ring is here | 40-23 liner | 40-23 | 40-23 | 40-23 hull wil be here | 40-23 | 40-23 hull 8/20 | 40-23 | 40-23 a/c lines romex and wire | 40-23 | 40-23 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-26 Deck transom first | 40-26 Deck | 40-26 Liner | 40-26 hull | 40-26 hull | 40-26 hull | 40-26 deck boat | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-29 | 40-29 | 40-29 | 40-29 | 40-29 | 40-29 | 40-29 | 40-30 | 40-30 | 40-30 | 40-30 | 40-30 | 40-30 | 40-30 | 40-31 | 40-31 | 40-31 | 40-31 | 40-31 | 40-31 | 40-31 | 40-32 | 40-32 | 40-32 | 40-32 | 40-32 | 40-32 | 40-32 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28
Finishing-Scheduled | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 | 40-23 | 40-23 | 40-23 | 40-23 | 40-23 | 40-23 | 40-23 | 40-23 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-28 | 40-28 | 40-28 | 40-28 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 |  |  |  | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 |  |  | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 |  |  | 40-29 | 40-29 | 40-29 | 40-29 | 40-29 | 40-29 |  | 40-30 | 40-30 | 40-30 | 40-30 | 40-30 | 40-30 | 40-31 |  |  | 40-31 | 40-31 | 40-31 | 40-31 | 40-31 | 40-31 |  | 40-32 | 40-32 | 40-32 | 40-32 | 40-32 | 40-32
Finishing-Actual | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-21 console,lp,ht | 40-21 console,lp,ht | 40-21 console,lp,ht hull | 40-21 console,lp,ht hull | 40-21 console,lp,ht hull | 40-21 | 40-21 | 40-21 | 40-21 | 40-21 | 40-21 | 40-21 | 40-21 | 40-21 | 40-22 | 40-22 console | 40-22 40-21 qc | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 |  |  |  | 40-22 hardtop ready monday | 40-23 small parts 40-22 hardtop | 40-23 small parts |  | 40-23 LP Hardtop | 40-23 small parts | 40-23 small parts | 40-23 small parts | 40-23 boat |  | 40-23 boat | 40-24 | 40-24 | 40-24 | 40-25 | 40-26 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-26 |  |  | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-27 |  |  | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 |  |  | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 |  |  | 40-29 | 40-29 | 40-29 | 40-29 | 40-29 | 40-29 |  | 40-30 | 40-30 | 40-30 | 40-30 | 40-30 | 40-30 | 40-31 |  |  | 40-31 | 40-31 | 40-31 | 40-31 | 40-31 | 40-31 |  | 40-32 | 40-32 | 40-32 | 40-32 | 40-32 | 40-32
Rigging-Scheduled | 40-21 | 40-21 | 40-21 | 40-21 | 40-21 | 40-21 | 40-21 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 | 40-23 | 40-23 | 40-23 | 40-23 | 40-23 | 40-23 | 40-23 | 40-23 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-22 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-27 | 40-27 | 40-27 | 40-27 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-27 | 40-28 | 40-26 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-29 | 40-29 | 40-29 | 40-29 | 40-29 | 40-29 | 40-29 | 40-29 | 40-30 | 40-30 | 40-30 | 40-30 | 40-30 | 40-30 | 40-30 | 40-30 | 40-31 | 40-31 | 40-31 | 40-31 | 40-31 | 40-31 | 40-31 | 40-31 | 40-32 | 40-32
Rigging-Actual | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-20 | 40-21 | 40-21 | 40-21 john wants console in at the end of week if possible | 40-21 leaning post needs to be in console needs to be in wed | 40-21 bilges need to be done hardtop install | 40-21 | 40-22 hardtop top wiring | 40-21 enignes here | 40-21 engines rigged | 40-22 | 40-21 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 t-top-finish JP | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 | 40-22 Frame | 40-22 lounge tub? top | 40-22 frame and top install | 40-23 finish upper | 40-23 | 40-23 | 40-23 | 40-23 | 40-23 | 40-23 | 40-23 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-24 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-25 | 40-26 | 40-26 | 40-26 | 40-26 | 40-26 | 40-27 | 40-28 | 40-26 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-27 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-28 | 40-29 | 40-29 | 40-29 | 40-29 | 40-29 | 40-29 | 40-29 | 40-29 | 40-30 | 40-30 | 40-30 | 40-30 | 40-30 | 40-30 | 40-30 | 40-30 | 40-31 | 40-31 | 40-31 | 40-31 | 40-31 | 40-31 | 40-31 | 40-31 | 40-32 | 40-32
Seatrial/qc-Scheduled | [6 empty] | 40-21 | [7 empty] | 40-22 | [8 empty] | 40-23 | [23 empty] | 40-25 | [7 empty] | 40-26 |  |  |  |  | 40-25 |  |  | 2026-04-13: 40-26; 2026-06-08: 40-27; 2026-08-03: 40-28; 2026-09-28: 40-29; 2026-11-23: 40-30 |  |  | 40-31
Seatrial/qc-Actual | [12 empty] | 40-20 | [8 empty] | 40-21 thur sea trial | 40-21 tue sea trial | [15 empty] | 40-22 | [5 empty] | 40-23 | [7 empty] | 40-24 | [7 empty] | 40-25 |  |  | 2026-04-13: 40-26; 2026-06-08: 40-27; 2026-08-03: 40-28; 2026-09-28: 40-29; 2026-11-23: 40-30 |  |  | 40-31
Detail/Delivery-Scheduled | [61 empty] | 40-25 |  | 2026-04-20: 40-26; 2026-06-15: 40-27; 2026-08-10: 40-28; 2026-10-05: 40-29; 2026-11-30: 40-30 |  |  |  | 40-31
Detail/Delivery-Actual | [13 empty] | 40-20 detail tues-3/25 | [8 empty] | 40-21 QC-tue-fri | 40-21 Detail-tues Final QC- wed | 40-21 Tue Delivery | [14 empty] | 40-22 | [5 empty] | 40-23 | [7 empty] | 40-24 | [7 empty] | 40-25 |  | 2026-04-20: 40-26; 2026-06-15: 40-27; 2026-08-10: 40-28; 2026-10-05: 40-29; 2026-11-30: 40-30 |  |  |  | 40-31
[36 empty] | Thursday Cookout For Labor Day- Employee handbook handout? | Labor Day off Mon | [11 empty] | Thanksgiving thur 11/27 off Thur and Fri | J.T. on vacation |  |  | Christmas Eve and Day off Wed,Thur,Fri | New Years Eve and Day off Wed,Thur ,Fri
Date of end of week | 12/27/2024 work 23,26,27 | 1/3/2025 work 30,2,3 | 1/10 | 1/17 | 1/24 | 1/31 | 2/7 | 2/14 | 2/21 | 2/28 | 3/7 | 3/14 | 3/21 | 3/28 | 4/4 | 4/11 | 4/18 | 4/25 | 4/28-5/2 | 5/5-5/9 | 5/12-5/16 | 5/19-5/23 | 5/26-lmemorial day 5/27-5/30 | 6/2-6/6 | 6/9-6/13 | 6/16-6/20 | 6/23-6/27 | 6/30-7/4 JT gone 6/30 | 7/7 off 7/8-massive clean up 7/9-7/11 | 7/14-7/18 | 7/21-7/25 | 7/28-8/1 | 8/4-8/8 | 8/11-8/15 | 8/18-8/22 | 8/25-8/29 | 9/2-9/5 | 9/8-9/12 | 9/15-9/19 | 9/22-9/26 | 9/29-10/3 | 10/6-10/10 | 10/13-10/17 | 10/20-10/24 | 10/27-10/31 | 11/7 | 11/14 | 11/21 | 11/28 | 12/5 | 12/12 | 12/19 | 12/22 & 12/23 | 12/29 & 12/30 | 1/5/26-1/9/26 | 1/12/2026-1/16/27 | 1/19/26-1/23/26 | 1/26/26-1/30/26 | 2/2-2/6 | 2/9-2/13 | 2/16-2/20 | 2/23-2/27 | 3/2-3/6 | time axis 2026-03-09 to 2026-12-28
Lamination-Scheduled | Delgado | Songy | Songy | Songy | Songy | Parks | Parks | Parks
Lamination-Actual | Goldman | Goldman- t | Goldman | Goldman Magrisso-tubs/liner,deck | Goldman | Magrisso-hull,small parts | Magrisso,stringers in hull ,small parts sims stringers | Bannan-liner and deck- new kits from mahogany liner has aquasteel and 3/4" core and deck has coosa |  | Brannan-hull spray | Brannan-hull/stringers | deck and liner | McCarthy deck and liner-glass was mahogany og core fgci Stringers | McMcarthy Hull | McMcarthy Hull/stringers | Russ-deck and liner | Russ-Hull | Russ-Hull/Stringers order wed-Mahogany og glass and new core-aquasteel!!!!!1 | Faccibene deck-coosa in back aquasteel in front and liner-aqua steel | Faccibene Small parts | Faccibene Hull-in hous ecore and glass | Hull/Stringers Deck/ Mahogany deck new all | Liner Mahogany liner new all | misc small parts and catchup | Swan Deck smal parts | Swan Hull mahogany hull glass and core Tubs | Swan Hull stringers Liner | Kennedy Hull-aquamist | Hull stringers Parks Deck | Parks Hull-kingston grey King- Deck | Parks Liner hull/stringers | King Hull-fighting lady yellow | King Hull stringers Liner | Smoak Deck | Smoak /liner tubs | Smoak Hull | filler for 40 and finishing items Stringers | Johnson Liner Tubs | Johnson Hull | Johnson Deck Stringers | Orme Liner Tubs | Orme Hull | Orme Hull stringers Deck Stringers | Fordon Liner tubs | Fordon Hull | Fordon Hull stringers Deck Stringers | King Liner tubs | King Hull | King Hull stringers Deck | Dunn Liner | Dunn Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck | Liner tubs | Hull | Hull stringers Deck
Assembly-Scheduled | Sims | Sims | Sims | Sims | Delgado | Delgado | Delgado | Songy | Magrisso | Magrisso | Brannan | Brannan | Brannan | [6 empty] | Mahogany og glass and new core | [6 empty] | mahogany hull glass and core | [5 empty] | Deck
Assembly-Actual | Sheffield | Songy- almost no one here | Songy | Songy | Songy | Goldman | Goldman | Goldman | Magrisso | Magrisso | Magrisso/Brannan | Brannan | Brannan | Brannan | McCarthy | McCarthy | McCarthy | McCarthy | Russ | Russ | Russ | Faccibene | Faccibene | Faccibene | Faccibene | Faccibene Work on matterhorn if time Swan deck to lazaro tue | Swan Deck/hull | Swan Liner | Kennedy | Swan decked by end of week | Kennedy | Kennedy | Kennedy / Parks | Parks | Parks / King | King | King | King/Smoak | Smoak | Smoak | Johnson | Johnson | Johnson | Orme | Orme | Orme | Fordon | Fordon | Fordon | King | King | King | Dunn | Dunn | Dunn
Finishing-Scheduled | ? | ? | ? | ? | Sims | Sims | Sims | Delgado | Magrisso | Magrisso | Magrisso | Parks | Parks
Finishing-Actual | Fisher | Fisher | Sheffield | Sheffield | Sheffield | Songy | Songy | Songy | Goldman | Goldman | Goldman | Magrisso | Magrisso | Magrisso | Magrisso | Brannan | Brannan-wed 830 3m abarssives test | Brannan | McCarthy | McCarthy | McCarthy | Russ | Russ-boat in finish | Russ | Faccibene-small parts | Faccibene-small parts | Faccibene-boat start qc wed for russ | Swan all small parts | Swan Boat | Swan Kennedy small aprts | Swan Kennedy small aprts | Swan Kennedy small parts | Kennedy Boat | Kennedy | Parks | Parks Boat Needs to be on Trailer w/ Motor Hung | Parks | King | King | King | Smoak | Smoak | Smoak | Johnson | Johnson | Johnson | Orme | Orme | Orme | Fordon | Fordon | Fordon | King | King | King | Dunn | Dunn | Dunn
Rigging-Scheduled | ? | ? | ? | ? | Sims | Sims | Sims | Delgado | Goldman | Goldman | Magrisso | Magrisso | Magrisso | Brannan | Brannan | Brannan
Rigging-Actual | Fisher - finishing parr no one here | Parr | Fisher | Fisher | Fisher | Sheffield | Sheffield | Sheffield | Songy | Songy | Songy-will potentially be pushed but right now on track-twin boats have always taken longer | Songy-will potentially be pushed but right now on track-twin boats have always taken longer | Songy/Goldman | Goldman | Goldman | Magrisso | Magrisso | Magrisso engine here on tuesday | Brannan console in wed am | Brannan tower | Brannan | McCarthy | McCarthy | McCarthy | Russ build console,lp,liner,top | Russ build console,lp,liner,top t-top end of week | Russ frame wil be here mon morning engine is here water by thur if not mon | Faccibene | Faccibene | Faccibene | Faccibene swan small parts | Swan swan small parts | Swan-hull | Swan | Kennedy | Kennedy | Kennedy | Parks | Parks | Parks | King | King | King | Smoak | Smoak | Smoak | Johnson | Johnson | Johnson | Orme | Orme | Orme | Fordon | Fordon | Fordon | King | King | King | Dunn | Dunn | Dunn
Seatrial/qc-Scheduled | Sheffield | [44 empty] | Smoak |  |  | Johnson |  |  | Orme | [5 empty] | King |  |  | Dunn | bar: 2026-03-09; 2026-03-30; 2026-04-20; 2026-05-11; 2026-06-01; 2026-06-22; 2026-07-13; 2026-08-03; 2026-08-24; 2026-09-14; 2026-10-05; 2026-10-26; 2026-11-16; 2026-12-07; 2026-12-28
Seatrial/qc-Actual |  |  |  |  | Fisher sea trial wed afternoon qc starting thursday |  |  | Sheffield-wed thur qc |  |  |  |  | Songy |  | Goldman |  |  | Magrisso |  |  | Brannan- QC-wed-fri |  |  | McCarthy tue call remarable |  |  | Russ |  |  | Faccibene | Faccibene |  |  | Swan |  |  | Kennedy |  |  | Parks |  |  | King |  |  | Smoak |  |  | Johnson |  |  | Orme |  | Probably a plant shutdown in here | Fordon |  |  | King |  |  | Dunn | bar: 2026-03-09; 2026-03-30; 2026-04-20; 2026-05-11; 2026-06-01; 2026-06-22; 2026-07-13; 2026-08-03; 2026-08-24; 2026-09-14; 2026-10-05; 2026-10-26; 2026-11-16; 2026-12-07; 2026-12-28
Detail/Delivery-Scheduled |  | Sheffield | bar: 2026-03-16; 2026-04-06; 2026-04-27; 2026-05-18; 2026-06-08; 2026-06-29; 2026-07-20; 2026-08-10; 2026-08-31; 2026-09-21; 2026-10-12; 2026-11-02; 2026-11-23; 2026-12-14
Detail/Delivery-Actual |  |  | Parr |  |  | Fisher qc finish monday detail tuesday final qc wed delivery thursday or friday |  |  | Sheffield qc finish monday detail tuesday final qc wed delivery thursday or friday |  |  |  | Songy-detail thur 3/20 | Songy-here wed 3/26 |  | Goldman thur-detail |  |  | Magrisso- engine mon seatrial tuesday detail wed final qc thursday delivery fri |  |  | Brannan Wed- detail scheduled Final QC- thur delivery fri |  |  | McCarthy issues with yamaha sea trial-fri | McCarthy Detail-mon final QC-tue Delivery wed-fri |  | Russ seatrial tmonday detail tue final qc twed-8ish ktm delivery thur |  |  | everything moved a week over |  | Faccibene engine mon seatrial tuesday detail wed final qc thursday delivery fri |  | Faccibene engine- wed seatiral thur | Faccibene mon detail tue- Final QC wed-Delivery Swan tue-seatrial wed detail thur-Final QC fri-Delivery |  | Kennedy |  |  | Parks |  |  | King |  |  | Smoak |  |  | Johnson |  |  | Orme |  |  | Fordon |  |  | K King |  |  | Dunn |  | 2026-03-16: Simms

## Core and Glass Kit deadlines
Mahogany Schedule-updated 5/28/25
Date | Hull Core & E-Glass | Deck Core & E-Glass | Liner Core & E-Glass
2025-06-19 |  |  | X
2025-06-26 | X-core
2025-07-03 |  |  | X
2025-07-10 | X | X-glass
2025-07-17 |  |  | X-core
2025-07-24 | X
2025-07-31 |  | X-glass
2025-08-07 |  |  | X
2025-08-14 | X
2025-08-21 |  | X
2025-08-28 |  |  | X
2025-09-04 | X
2025-09-11 |  | X
2025-09-18 |  |  | X
2025-09-25 | X
2025-10-02 |  | X
2025-10-09 |  |  | X
2025-10-16 | X
2025-10-23 |  | X
2025-10-30 |  |  | X
2025-11-06 | X
2025-11-13 |  | X
2025-11-20 |  |  | X
2025-11-27 | X
2025-12-04 |  | X
2025-12-11 |  |  | X
2025-12-18 | X
2025-12-25 |  | X

## Sheet1 (hidden)
Date | 2025-04-25 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07
Things to do | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts | check on all depts
Things to do | 2025-04-28: get ready for meeting; 2025-04-30: get ready for meeting; 2025-05-05: get ready for meeting; 2025-05-07: get ready for meeting; 2025-05-12: get ready for meeting; 2025-05-14: get ready for meeting; 2025-05-19: get ready for meeting; 2025-05-21: get ready for meeting; 2025-05-26: get ready for meeting; 2025-05-28: get ready for meeting; 2025-06-02: get ready for meeting; 2025-06-04: get ready for meeting; 2025-06-07: get ready for meeting |  | get ready for meeting |  |  | get ready for meeting |  | get ready for meeting |  |  | get ready for meeting | get ready for meeting
Things to do | 2025-04-28: 8am meeting; 2025-04-30: 8am meeting; 2025-05-05: 8am meeting; 2025-05-07: 8am meeting; 2025-05-12: 8am meeting; 2025-05-14: 8am meeting; 2025-05-19: 8am meeting; 2025-05-21: 8am meeting; 2025-05-26: 8am meeting; 2025-05-28: 8am meeting; 2025-06-02: 8am meeting; 2025-06-04: 8am meeting; 2025-06-07: 8am meeting |  | 8am meeting |  |  | 8am meeting |  | 8am meeting |  |  | 8am meeting | 8am meeting
Things to do | 2025-04-28: 9am meeting; 2025-04-30: 9am meeting; 2025-05-05: 9am meeting; 2025-05-07: 9am meeting; 2025-05-12: 9am meeting; 2025-05-14: 9am meeting; 2025-05-19: 9am meeting; 2025-05-21: 9am meeting; 2025-05-26: 9am meeting; 2025-05-28: 9am meeting; 2025-06-02: 9am meeting; 2025-06-04: 9am meeting; 2025-06-07: 9am meeting |  | 9am meeting |  |  | 9am meeting |  | 9am meeting |  |  | 9am meeting | 9am meeting
Things to do
Things to do
Things to do
Things to do
Things to do
Things to do
Things to do
Things to do
Things to do
Things to do
Things to do
Things to do
Things to do
Things to do

## Detail Schedule (hidden)
Detail Schedule
Dates Tue or Wed is always the goal | 26 | 40
4/28-5/2 | X
5/19-5/23 | X | X
6/9-6/13 | X
6/30-7/4 | X
7/14-7/18 |  | X
7/21-7/25 | X
8/11-8/15 | X
9/1-9/5 | X
9/8-9/12 |  | X
9/22-9/26 | X
10/13-10/17 | X
11/3-11/7 | X | X
11/24-11/28 | X
12/15-12/19 | X

## core,glass,gelcoat deadlines (hidden)
Mahogany Schedule
Date | Hull Core & E-Glass | Deck Core & E-Glass | Liner Core & E-Glass | Gelcoat Color Needed by
2025-04-29 |  | X | X
2025-05-27 |  | X | X
2025-06-05 | X |  |  | 2025-05-08
2025-06-19 |  | X | X
2025-06-26 | X |  |  | 2025-05-29
2025-07-10 |  | X | X
2025-07-17 | X |  |  | 2025-06-19
2025-07-31 |  | X | X
2025-08-07 | X |  |  | 2025-07-10
2025-08-21 |  | X | X
2025-08-28 | X |  |  | 2025-07-31
2025-09-11 |  | X | X
2025-09-18 | X |  |  | 2025-08-21
2025-10-02 |  | X | X
2025-10-09 | X |  |  | 2025-09-11
2025-10-23 |  | X | X
2025-10-30 | X |  |  | 2025-10-02
2025-11-13 |  | X | X
2025-11-20 | X |  |  | 2025-10-23
2025-12-04 |  | X | X
2025-12-11 | X |  |  | 2025-11-13
2025-12-25 |  | X | X
Formulas:
Date = [Date, row above]+14

## Sheet2
40-21
Task/Part: |  | need to make | 5/27-5/30 | 6/2-6/6 | 6/9-6/13 | 6/16-6/20 | 6/23-6/27 | 6/30-7/4 | 7/11 | 7/18
Console | 3 weeks | 2 | Ro | X
Console Liner | 3.25 | 1 | X
Hard Top/ Pie Plates | 3 |  |  | ? | ? | ? | ? | ? | ? | ? | reinaldo
Leaning Post | 1.8 |  |  | ? | ? | ? | ? | ? | ? | ? | romero
Hatches | 2.3 |  |  | ? | ? | ? | ? | ? | ? | ? | jensey
Speaker Rings 2-10 | [10 empty] | yoandi
Console Trim-need | 0.5 | [9 empty] | josdonny
Pre-Rigging Finish hull | 3.5 |  | r/y | JO | JO | JO | JO |  |  |  | natalia
liner | 4 |  | X | X | X | X |  |  |  |  | brian
deck | 2 |  |  |  | X | X |  |  |  |  | oscar
Final Finish | [10 empty] | budy
Warranty/ Misc.
dive doors | 4.8 |  | JO | JO | JO | JO | JO
Tubs
Rod Lockers-need | 0.5
teaser reels-need
Pie Plates-need
Lounge Tub-send out
Transom Deck | 1.6 |  | - | - | - | - | - | - | - | -
dive door frame inside and outside |  |  | JO | JO | JO | JO | JO
pull cooler sorround | [11 empty] | 1250 | 1241 | 1806 | 1432
40-21 QC |  |  | NAT,YO,BUDY | [11 empty] | 159 pp
|  |  | 4 | 4 people | 4 people | 4 people | 1 person | [7 empty] | 4 weeks
Task/Part: | avg hours |  | 5/27-5/30 | 6/2-6/6 | 6/9-6/13 | 6/16-6/20 | 6/23-6/27 | 6/30-7/4 | 7/11 | 7/18
Console | 38.9 | 1 | O | 0/
Console Liner | 28.6 | 0.75 | -
Hard Top/ Pie Plates | 39.2 | 1 | -
Upper Helm | 13.4 | 0.25
Leaning Post | 46.1 | 1 |  | X
Hatches | 134.4 | 3.25 | B/bu | B/bu
Speaker Rings | 11.6
Console Trim | 30.4 | 0.75
Drop-in Bucket | 4.9
Pre-Rigging Finish-hull | 32 | 0.8
hull bottom | 21.2 | 0.5
liner | 68.4 | 1.7 | JEN | JEN
deck | 18.8 | 0.5 | JEN
Final Finish | 23.1 | 0.5
Warranty/ Misc. | 7.2
Tubs | 6.9
seachest | 0.4
Fuel access plate | 3
|  |  | 4 | 3